|  |  |  |
| --- | --- | --- |
| Day | Task | Complete |
| 29th November | Finish mock-ups | Yes |
| 30th  | Plan photoshoot | Yes |
| 1st December | Take pictures | Yes |
| 2nd  | Take pictures, begin to edit | Yes |
| 3rd | Edit and input pictures into the pages | Yes |
| 4th | Design work – Front Cover | Yes |
| 5th | “ “ | Yes |
| 6th | Design work – Contents Page | Yes |
| 7th | “ “ | Yes |
| 8th | Write Double Page Spread article | Yes |
| 9th | “ “ | Yes |
| 10th | Design work – Double Page Spread | Yes |
| 11th | “ “ | Yes |
| 12th | Finalise, collect all work and make sure it is all complete | Yes |
| 13th | Contingency | Yes |
| 14th | “ “ | Yes |
| 15th | Evaluation | Yes |
| 16th | Upload everything to Weebly Site and annotate | Yes |